## Tasks
Name - Original | Name | Id | Hierarchy Level | Start Date | Finish Date | Actual Start Date | Actual Finish Date | Pct Completed | Unique Id | ParentTaskId
'b4ubuild_sample_07a | b4ubuild_sample_07a | 0 | 0 | 2008-01-06 | 2008-03-09 |  |  | 0 | 0 | -1
' Contracts | Contracts | 1 | 1 | 2008-01-06 08:00 | 2008-01-21 08:00 |  |  | 0 | 145 | 0
' Supply Lot Sale Agreement | Supply Lot Sale Agreement | 2 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 287 | 145
' Supply Construction Agreement | Supply Construction Agreement | 3 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 273 | 145
' Supply Contract Plans | Supply Contract Plans | 4 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 2 | 145
' Supply Contract Specifications | Supply Contract Specifications | 5 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 262 | 145
' Supply Contract Site Plan | Supply Contract Site Plan | 6 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 3 | 145
' Secure Financing | Secure Financing | 7 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 289 | 145
' Construction Loan Settlement | Construction Loan Settlement | 8 | 2 | 2008-01-06 | 2008-01-21 |  |  | 0 | 290 | 145
' Document Review & Revision | Document Review & Revision | 9 | 1 | 2008-02-06 | 2008-02-21 |  |  | 0 | 274 | 0
' Review & Finalize Plans | Review & Finalize Plans | 10 | 2 | 2008-02-06 | 2008-02-21 |  |  | 0 | 275 | 274
' Review & Finalize Specifications | Review & Finalize Specifications | 11 | 2 | 2008-02-06 | 2008-02-21 |  |  | 0 | 276 | 274
' Review & Finalize Site Plan | Review & Finalize Site Plan | 12 | 2 | 2008-06-23 | 2008-07-08 |  |  | 0 | 277 | 274
' Print Construction Drawings | Print Construction Drawings | 13 | 2 | 2008-06-30 | 2008-07-15 |  |  | 0 | 282 | 274
' Approve Revised Plans | Approve Revised Plans | 14 | 2 | 2008-07-04 05:00 | 2008-07-19 05:00 |  |  | 0 | 284 | 274
' Approve Revised Specifications | Approve Revised Specifications | 15 | 2 | 2008-04-07 | 2008-04-22 |  |  | 0 | 285 | 274
' Approve Revised Site Plan | Approve Revised Site Plan | 16 | 2 | 2008-04-07 | 2008-04-22 |  |  | 0 | 291 | 274
' Bids & Contracts | Bids & Contracts | 17 | 1 | 2008-07-07 | 2008-07-22 |  |  | 0 | 4 | 0
' Make Copies of Plans | Make Copies of Plans | 18 | 2 | 2008-07-07 | 2008-07-22 |  |  | 0 | 146 | 4
' Make Copies of Specifications | Make Copies of Specifications | 19 | 2 | 2008-07-07 | 2008-07-22 |  |  | 0 | 278 | 4
' Distribute Plans & Specifications | Distribute Plans & Specifications | 20 | 2 | 2008-10-07 | 2008-10-22 |  |  | 0 | 5 | 4
' Receive Bids | Receive Bids | 21 | 2 | 2008-11-07 | 2008-11-22 |  |  | 0 | 6 | 4
' Review Bids | Review Bids | 22 | 2 | 2008-07-25 | 2008-08-09 |  |  | 0 | 7 | 4
' Sales | Sales | 23 | 3 | 2008-07-25 | 2008-08-09 |  |  | 0 | 279 | 7
' Construction | Construction | 24 | 3 | 2008-07-25 | 2008-08-09 |  |  | 0 | 280 | 7
' Execute Subcontractor Agreements | Execute Subcontractor Agreements | 25 | 2 | 2008-01-08 | 2008-01-23 |  |  | 0 | 8 | 4
' Grading & Building Permits | Grading & Building Permits | 26 | 1 | 2008-07-07 | 2008-07-22 |  |  | 0 | 9 | 0
' Schedule lot stake-out | Schedule lot stake-out | 27 | 2 | 2008-07-07 | 2008-07-22 |  |  | 0 | 10 | 9
' Stake lot | Stake lot | 28 | 2 | 2008-11-07 | 2008-11-22 |  |  | 0 | 11 | 9
' File Grading Permit Application | File Grading Permit Application | 29 | 2 | 2008-07-07 | 2008-07-22 |  |  | 0 | 293 | 9
' File Building Permit Application | File Building Permit Application | 30 | 2 | 2008-07-07 | 2008-07-22 |  |  | 0 | 12 | 9
' Post Lot Identification | Post Lot Identification | 31 | 2 | 2008-07-14 | 2008-07-29 |  |  | 0 | 13 | 9
' Meet Sediment Control Inspector | Meet Sediment Control Inspector | 32 | 2 | 2008-07-15 | 2008-07-30 |  |  | 0 | 15 | 9
' Walk Lot w/ Owner | Walk Lot w/ Owner | 33 | 2 | 2008-07-16 | 2008-07-31 |  |  | 0 | 14 | 9
' Install Construction Entrance | Install Construction Entrance | 34 | 2 | 2008-07-17 | 2008-08-01 |  |  | 0 | 16 | 9
' Install Sediment Controls | Install Sediment Controls | 35 | 2 | 2008-07-17 | 2008-08-01 |  |  | 0 | 153 | 9
' Sediment Control Insp. | Sediment Control Insp. | 36 | 2 | 2008-07-21 | 2008-08-05 |  |  | 0 | 17 | 9
' Grading Permit Issued | Grading Permit Issued | 37 | 2 | 2008-07-22 | 2008-08-06 |  |  | 0 | 18 | 9
' County Permit Process | County Permit Process | 38 | 2 | 2008-10-07 | 2008-10-22 |  |  | 0 | 147 | 9
' Building Permit Approved | Building Permit Approved | 39 | 2 | 2008-07-24 | 2008-08-08 |  |  | 0 | 19 | 9
' Pay Permit Fees and Excise Taxes | Pay Permit Fees and Excise Taxes | 40 | 2 | 2008-07-25 | 2008-08-09 |  |  | 0 | 281 | 9
' Building Permit Issued | Building Permit Issued | 41 | 2 | 2008-07-26 | 2008-08-10 |  |  | 0 | 294 | 9
' Site Work | Site Work | 42 | 1 | 2008-07-27 | 2008-08-11 |  |  | 0 | 20 | 0
' Clear Lot | Clear Lot | 43 | 2 | 2008-07-28 | 2008-08-12 |  |  | 0 | 21 | 20
' Strip Topsoil & Stockpile | Strip Topsoil & Stockpile | 44 | 2 | 2008-07-29 | 2008-08-13 |  |  | 0 | 22 | 20
' Stake Lot for Excavation | Stake Lot for Excavation | 45 | 2 | 2008-07-30 | 2008-08-14 |  |  | 0 | 23 | 20
' Rough grade lot | Rough grade lot | 46 | 2 | 2008-07-31 | 2008-08-15 |  |  | 0 | 24 | 20
' Excavate for foundation | Excavate for foundation | 47 | 2 | 2008-08-01 | 2008-08-16 |  |  | 0 | 25 | 20
' Foundation | Foundation | 48 | 1 | 2008-08-02 | 2008-08-17 |  |  | 0 | 26 | 0
' Layout footings | Layout footings | 49 | 2 | 2008-08-03 | 2008-08-18 |  |  | 0 | 27 | 26
' Dig Footings & Install Reinforcing | Dig Footings & Install Reinforcing | 50 | 2 | 2008-08-04 | 2008-08-19 |  |  | 0 | 28 | 26
' Footing Inspection | Footing Inspection | 51 | 2 | 2008-08-05 | 2008-08-20 |  |  | 0 | 29 | 26
' Pour footings | Pour footings | 52 | 2 | 2008-08-06 | 2008-08-21 |  |  | 0 | 30 | 26
' Pin Footings | Pin Footings | 53 | 2 | 2008-08-07 | 2008-08-22 |  |  | 0 | 31 | 26
' Stock Block, Mortar, Sand | Stock Block, Mortar, Sand | 54 | 2 | 2008-08-08 | 2008-08-23 |  |  | 0 | 32 | 26
' Build Block Foundation | Build Block Foundation | 55 | 2 | 2008-08-09 | 2008-08-24 |  |  | 0 | 33 | 26
' Foundation Certification | Foundation Certification | 56 | 2 | 2008-08-10 | 2008-08-25 |  |  | 0 | 35 | 26
' Draw #1 (Location Survey) | Draw #1 (Location Survey) | 57 | 2 | 2008-08-11 | 2008-08-26 |  |  | 0 | 310 | 26
' Fill Block Cores w/ Concrete | Fill Block Cores w/ Concrete | 58 | 2 | 2008-08-12 | 2008-08-27 |  |  | 0 | 36 | 26
' Steel Delivery | Steel Delivery | 59 | 2 | 2008-08-13 | 2008-08-28 |  |  | 0 | 34 | 26
' Set Lintels, Bolts, Cap Block | Set Lintels, Bolts, Cap Block | 60 | 2 | 2008-08-14 | 2008-08-29 |  |  | 0 | 37 | 26
' Lumber Delivery | Lumber Delivery | 61 | 2 | 2008-08-15 | 2008-08-30 |  |  | 0 | 39 | 26
' Waterproofing and Drain Tile | Waterproofing and Drain Tile | 62 | 2 | 2008-08-16 | 2008-08-31 |  |  | 0 | 38 | 26
Formulas:
Finish Date = Table1[[#This Row],[Start Date]]+15

## Resources
Name | Id | Unique Id | Initials | Group
Sales Department | 1 | 1 | S
Construction Dept. | 2 | 2 | C
Sales Dept. | 3 | 3 | S
Client | 4 | 10 | C
County | 5 | 13 | C
County Sediment Control Inspector | 6 | 14 | C
Sediment Control Inspector | 7 | 15 | S
Department of Permits & Licenses | 8 | 16 | D
Building Inspector | 9 | 19 | B
Mason | 10 | 20 | M
Civil Engineer | 11 | 21 | C
Concrete Subcontractor | 12 | 22 | C
Concrete Subcontractor | 13 | 23 | C
Excavation Subcontractor | 14 | 24 | E
Masonry Subcontractor | 15 | 25 | M
Block Masonry Subcontractor | 16 | 26 | B
Steel Supplier | 17 | 27 | S
Lumber Supplier | 18 | 28 | L
Waterproofing Subcontractor | 19 | 29 | W
Lender | 20 | 30 | L
Framing Subcontractor | 21 | 31 | F
Pest Control Subcontractor | 22 | 32 | P
Mechanical Subcontractor | 23 | 33 | M
Plumbing Subcontractor | 24 | 34 | P
Field Superintendent | 25 | 35 | F
Plumbing Inspector | 26 | 36 | P
Electrical Subcontractor | 27 | 37 | E
Alarm Subcontractor | 28 | 38 | A
Client's Subcontractor | 29 | 39 | C
Electrical Inspector | 30 | 40 | E
Roofing Subcontractor | 31 | 41 | R
Exterior Trim Subcontractor | 32 | 42 | E
Brick Masonry Subcontractor | 33 | 44 | B
Insulation Subcontractor | 34 | 45 | I
BGE Inspector | 35 | 46 | B
Drywall Subcontractor | 36 | 47 | D
Painting Subcontractor | 37 | 48 | P
Trim Supplier | 38 | 49 | T
Interior Trim Subcontractor | 39 | 50 | I
Cabinet Subcontractor | 40 | 51 | C
Deck Subcontractor | 41 | 54 | D
Driveway Subcontractor | 42 | 55 | D
Seeding Subcontractor | 43 | 56 | S
Hardware Subcontractor | 44 | 57 | H
Mirror Subcontractor | 45 | 58 | M
Tile Subcontractor | 46 | 59 | T
Hardwood Floor Subcontractor | 47 | 60 | H
Carpet Subcontractor | 48 | 61 | C
Department of Licensing & Permits | 49 | 62 | D
Paint Subcontractor | 50 | 63 | P
Window Cleaning Subcontractor | 51 | 64 | W
Cleaning Subcontractor | 52 | 65 | C
Superintendent | 53 | 66 | S
Builder | 54 | 67 | B
Punch Out Crew | 55 | 68 | P
Stucco Subcontractor | 56 | 69 | S
Sales Manager | 57 | 70 | S
Construction Manager | 58 | 71 | C
Project Manager | 59 | 72 | P